## Sheet1
Risk ID | Risk Category | Risk Name | Risk Description | Affected Use Cases | Likelihood | Impact | Owner | Controls | Treatment | Status | Evidence
SB - 01 | Strategic and Business | Vendor Lock-In | Reliance on a single external AI provider for critical systems could limit flexibility, drive up costs, and create dependency risks. If the vendor changes pricing, availability, or terms of service, the organization’s ability to adapt may be compromised. | FraudGuard, AssistPal | 2 | 3 | AI Team 1 | SBC - 01, SBC - 5, SBC - 10 | Acceptance | Treated | Control Library Document - Strategic/Business Risks Section
OT - 01 | Operational and Technical | Model Drift | AI models may lose accuracy over time due to changes in data patterns or environments. Without proper monitoring and retraining, this can result in poor performance, incorrect decisions, and inefficiencies across business processes. | [5 empty] | Mitigation | In Progress
EB - 01 | Ethical and Bias | Discriminatory Hiring Recommendations | An AI-driven recruitment system may unintentionally favor or exclude candidates based on gender, race, or age due to biased training data. This could lead to unfair treatment of applicants and damage the organization’s commitment to diversity and inclusion. | [5 empty] | Avoidance | Not Started
SP - 01 | Security and Privacy | PII Exposure | AI systems trained on personal or customer data may inadvertently expose sensitive information (e.g., health records, financial data). This could occur through adversarial attacks, poor anonymization, or re-identification, leading to data breaches and loss of trust. | [5 empty] | Transferrence | Treated
RR - 01 | Regulatory and Reputational | EU AI Act Non Compliance | Deploying AI systems classified as “high-risk” under the EU AI Act without required documentation, testing, or human oversight could result in significant fines, regulatory sanctions, and reputational harm, especially if the failure is publicized. | [5 empty] | Avoidance | Treated